## Sheet1
Risk Register for Project Name
Date
Project Name: Student Enrolment Management
ID No. | Rank | Risk | Solution | Category | Root Cause | Risk Owner | Probability | Impact | Status
1 | 1 | Customer requires more interfacing to manage than planned | Project organization setup with a development manager to focus on the team's work, leaving project manager time to focus on client. | Communication |  | PM | 1 | 1 | potential
2 | 8 | Some Stakeholders are too busy and often not available on critical communication. | Manager always need to plan ahead and building Scope and Plan with flexibility and reflecy with any changes in schedules. | Communication |  | PM | 2 | 4 | potential
3 | 12 | Unobvious requirement from customer | Talk more to customer, use more survey | Communication | lack of experience communicates with customers | BA | 2 | 6 | active
4 | 28 | Member couldn't finish their task before the deadline | Hire more member for loosing their deadlines | Time | Member may get sick. To much dealine | PM | 7 | 4 | potential
5 | 15 | Design cost more time than expected, delayed the deadline lead to project jamming | Manager always need to plan ahead and building Scope and Plan with flexibility and reflecy with any changes in schedules. | Time | Estimate not accurate | PM | 5 | 3 | active
6 | 12 | Scope changes may not be processed through the change control process. | Ensure QC will get informed about changes process change control | Scope |  | BA | 6 | 2 | potential
7 | 4 | The project team may not identify all the deliverables, requiring changes later. | Assign a control management task to define and identify the changes in requirement | Scope | There are no inform to the project team | PM | 4 | 1 | potential
8 | 9 | Individuals may add features to the product that were not approved. | Ensure team members informed well about approved features | Scope | individuals do not get the requirements | PM | 3 | 3 | potential
9 | 30 | System integration more complex than estimated. | Expend more development effort, try and minimize this by regular meetings between development and integration teams. | Integration |  | PM | 6 | 5 | potential
10 | 12 | Low-security services of hosting service | Hire a security tester to ensure security | Integration |  | PM | 4 | 3 | potential
11 | 6 | Database connection not working properly | Assign DB related parts to members that has enough knowledge. In worse case senario, hire some professional to train some members to work with db. | Integration |  | DEV | 2 | 3 | potential
12 | 20 | The server capacity initially defined may be inadequate. | Purchase and install additional disc space at the customer site. | Resource | Estimate not accurate | BA | 4 | 5 | potential
13 | 6 | Staff reject new procedures | Provide opportunity for staff feedback prior to policy/procedure finalisation; Develop Training Plan that allows for repeat attendance (perhaps 2 stage training) | Resource |  | BA | 3 | 2 | potential
14 | 9 | Problems with Computer likes Windows errors, Ram or CPU not working correctly,... | Always pay attention to hardware and software problems, report immediately if found out any to minimize the delay. | Resource |  | DEV | 3 | 3 | potential
15 | 9 | Poor planning and resources divide lead to late in progress due to some project members got sick. | Manager always need to plan ahead and building Scope and Plan with flexibility and reflecy with any changes in schedules. | Resource |  | PM | 3 | 3 | potential
16 | 28 | Inadequate funding to complete the project | Re-scope project, focusing on time and resourcing | Cost |  | PM | 7 | 4 | active
17 | 16 | System Design Structure is tangled and hard to maintain | Refactor the design document to optimize software structure | Quality |  | DEV | 4 | 4 | potential