## Sheet1
Cost Estimate
Project Name: | Date:
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 24 | 35 | 840 |  | 0 | 0 | 840 | 0 | 840
2. Planning | 48 | 40 | 1920 |  | 0 | 0 | 1920 | 0 | 1920
3. Executing | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3.1 Project Kickoff Metting |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
3.2 Verify and Validate User Requirements | 36 | 20 | 720 | 0 | 0 | 0 | 720 | 0 | 720
3.3 Design System |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
3.3.1 Design Database Structure | 40 | 35 | 1400 | 0 | 0 | 0 | 1400 | 0 | 1400
3.3.2 Design Particular Database | 40 | 45 | 1800 | 0 | 0 | 0 | 1800 | 0 | 1800
3.3.3 Design Overview Functional Structure | 40 | 40 | 1600 | 0 | 0 | 0 | 1600 | 0 | 1600
3.3.4 Design Detailed Functional Components | 40 | 40 | 1600 | 0 | 0 | 0 | 1600 | 0 | 1600
3.3.5 Design UI/UX | 80 | 30 | 2400 | 0 | 0 | 0 | 2400 | 0 | 2400
3.3.6 Test Planning | 40 | 30 | 1200 | 0 | 0 | 0 | 1200 | 0 | 1200
3.3.7 Test Design | 40 | 35 | 1400 | 0 | 0 | 0 | 1400 | 0 | 1400
3.4 Procure Hardware/Software | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200
3.5 Develop System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.1 Develop Database | 40 | 25 | 1000 | 0 | 0 | 0 | 1000 | 0 | 1000
3.5.2 Develop Functions | 80 | 20 | 1600 | 0 | 0 | 0 | 1600 | 0 | 1600
3.5.3 Develop UI/UX | 80 | 25 | 2000 | 0 | 0 | 0 | 2000 | 0 | 2000
3.6 Install Development System | 38 | 15 | 570 | 0 | 0 | 0 | 570 | 400 | 970
3.7 Testing Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7.1 Test Database | 40 | 15 | 600 | 0 | 0 | 0 | 600 | 0 | 600
3.7.2 Test Functions | 40 | 20 | 800 | 0 | 0 | 0 | 800 | 0 | 800
3.7.3 Test UI | 40 | 20 | 800 | 0 | 0 | 0 | 800 | 0 | 800
3.7.4 Summarize Test Result | 30 | 25 | 750 | 0 | 0 | 0 | 750 | 150 | 900
3.8 Fix Bugs | 40 | 35 | 1400 | 0 | 0 | 0 | 1400 | 0 | 1400
3.9 Setup Deployment | 40 | 25 | 1000 | 0 | 0 | 0 | 1000 | 1300 | 2300
3.10 Deploy System | 18 | 25 | 450 | 0 | 0 | 0 | 450 | 700 | 1150
4. Control | 66 | 40 | 2640 | 0 | 0 | 0 | 2640 | 0 | 2640
5. Closeout | 48 | 35 | 1680 | 0 | 0 | 0 | 1680 | 0 | 1680
32920