## Sheet1
Student Enrol Management RACI Chart
Date
Phrase | Task | Phùng Thanh Tú (CTO) | Nguyễn Tiến Đạt (CEO) | Trần Anh Tuấn (BA) | Developer | Tester | Sponsor
Initiation | 1.1. Evaluation & Recommendations | A/R | [5 empty] | R: Responsible
| 1.2. Develop Project Charter | R | I | I |  |  | A | A: Accountable
| 1.3. Deliverable: Submit Project Charter | I | A | R |  |  |  | C: Consulted
| 1.4. Project Sponsor Reviews Project Charter | I | I | A |  |  | R | I: Informed
| 1.5. Project Charter Signed/Approved | R | R | R |  |  | A/R
Planning | 2.1. Create Preliminary Scope Statement | A |  | R
| 2.2. Determine Project Team | A |  | R
| 2.3. Project Team Kickoff Meeting | A/R | R | R
| 2.4. Develop Project Plan | A | R
| 2.5. Submit Project Plan | A | R
| 2.6. Milestone: Project Plan Approval | A | R | I
Execution | 3.1 Project Kickoff Metting | R | R | R |  |  | A/R
| 3.2 Verify and Validate User Requirements | A | R | R
3.3 Design System
| 3.3.1 Design Database Structure |  | A | R | R
| 3.3.2 Design Particular Database | R | A |  | R
| 3.3.3 Design Overview Functional Structure |  | A | R | R
| 3.3.4 Design Detailed Functional Components | R | A |  | R
| 3.3.5 Design UI/UX |  | A | R | R
| 3.3.6 Test Planning | C | A |  |  | R
| 3.3.7 Test Design | C | A |  |  | R
| 3.4 Procure Hardware/Software | A |  | R
3.5 Develop System
| 3.5.1 Develop Database |  | R | A | R
| 3.5.2 Develop Functions | R |  | A | R
| 3.5.3 Develop UI/UX |  | R | A | R
| 3.6 Install Development System |  | I | A | R
3.7 Testing Phase
| 3.7.1 Test Database | C | A |  |  | R
| 3.7.2 Test Functions | C | A |  |  | R
| 3.7.3 Test UI | C | A |  |  | R
| 3.7.4 Summarize Test Result | A | I | I |  | R
| 3.8 Fix Bugs | A | C | C | R
| 3.9 Setup Deployment | A | C | C | R
| 3.10 Deploy System | C | A | R
Control | 4.1. Project Status Meetings | A/R | R | R
| 4.2. Summarize Risk | A | R | I
| 4.3. Create Update Plan | A | I | R
Closeout | 5.1. Audit Procurement |  | A | R
| 5.2. Document Lessons Learned | A | I | R
| 5.3. Update Files/Records | R | A | I
| 5.4. Gain Formal Acceptance | A | R | I
| 5.5. Archive Files/Documents | A | I | R